Sprint 2 — Pre-planning Artifacts

Timeline, Budget, Documentation Checklist, Risk Register

1. Project Timeline (working backwards from January 2027)

| Milestone | Target |
| --- | --- |
| Finalise internship shortlist and selection criteria | Complete |
| Submit application (Expat Globe — only listing still open) | Before 1 October 2026 |
| Interview / mock interview preparation | October 2026 |
| Offer accepted | October–November 2026 |
| Learning Agreement for Traineeships signed (self, DkIT, host) | November 2026 |
| Grant Agreement signed, funding confirmed | November–December 2026 |
| Accommodation booked | December 2026 |
| Travel booked | December 2026 |
| Departure | January 2027 |

Dependency chain: Application > Interview > Offer > Learning Agreement > Grant Agreement > Accommodation/Travel > Departure. Accommodation and travel can’t be safely committed to before the Learning Agreement is signed, since that’s what confirms the placement is real.

2. Budget

| Item | Cologne (Germany) | Valencia (Spain) |
| --- | --- | --- |
| Estimated monthly rent | €500–700 | €350–700 |
| Estimated other monthly costs (food, transport, utilities) | €300–400 | €250–350 |
| Estimated total monthly cost | €1,000 | €850 |
| Erasmus+ grant (Group 1 rate) | €700/month | €550/month (confirmed, Group 2) |
| Monthly shortfall | €300 | €300 |
| One-off setup costs (flights, deposit, insurance excess) | €800–1,000 | €500–700 |
| Deposit exposure | Up to 3 months’ rent | 1-2 months rent (legal cap) |

Grant note: Germany and Ireland are in Erasmus+ Group 1 (higher cost of living), which indicates a traineeship rate of about €700 per month. Since that internal inquiry was removed from the project, this is a well-sourced planned figure rather than a DkIT-specific confirmation. The €550 Group 2 rate for Spain is independently verified.

Funding gap mitigation: Personal savings are used to cover the monthly shortfall in both locations; one-time setup expenditures are budgeted separately as a lump sum required before to leave rather than being combined with monthly operating expenses.

3. Documentation Checklist

| Document | Status | Notes |
| --- | --- | --- |
| Passport | Not started | Check expiry — must be valid 6 months beyond return date |
| EHIC / GHIC | Not started | Free to apply for; renew if expired |
| Travel & health insurance | Not started | Compare Erasmus+-recommended providers |
| Learning Agreement for Traineeships | Blocked | Needs host confirmation + DkIT sign-off |
| Transcript of records | Not started | Request from DkIT records office |
| Europass CV | Done | See Gerard_McGreevy_CV.docx |
| Proof of address | Not started | Utility bill or bank statement |

4. Risk Register

| # | Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| 1 | Rejected by all three shortlisted placements | Medium | High | Widen search if Expat Globe falls through; keep monitoring ErasmusIntern | Self |
| 2 | Grant shortfall exceeds savings | Medium | High | Track actual living costs from month one; build buffer pre-departure | Self |
| 3 | Accommodation not secured before arrival | Medium | High | Start search immediately once placement confirmed; use platforms with payment protection | Self |
| 4 | ErasmusIntern platform discontinued before application completes | Low | Medium | Save all listing details locally now, not just links | Self |
| 5 | Remote/voluntary role (greentech) not eligible for Erasmus+ funding | Medium | Medium | Confirm with International Office before relying on this option | Self / DkIT |
| 6 | Rental fraud targeting incoming students | Low | High | Never transfer deposit before a viewing; use protected platforms | Self |
| 7 | Learning Agreement delayed by host or DkIT sign-off | Medium | Medium | Start Learning Agreement paperwork as soon as offer is accepted, not after | Self / DkIT |
| 8 | Language barrier outside the workplace | Medium | Low | Erasmus+ Online Language Support, 3 hrs/week before departure | Self |
| 9 | Actual Germany grant rate differs from the Group 1 planning figure | Low | Medium | Budget built on published group bands, not an institution-specific confirmation, since that enquiry was dropped; treat €700 as an estimate | Self |
| 10 | Module/timetable clash with a January 2027 departure | Low | Medium | Confirm with course coordinator whether a January start is compatible with academic calendar | Self / DkIT |

Top three by combined impact: #1 (rejection), #2 (grant shortfall), #3 (accommodation) are in the report.